## WBS
Work Breakdown Structure - Distribution and Contribution
Documentation
Setup and Configuration
all classes/codes/scripts (eg arrange by MVC)
[6 empty] | Model | [6 empty] | View | [5 empty] | Controller | [6 empty] | Interfaces (Misc) | Utils
Tasks Team Member | Class Diagram | Sequence Diagram | Presentation | Testing Doc | Final Report | Project.java | ProjectBuilder.java | User.java Applicant.java HDBOfficer.java HDBManager.java | Registration.java | Enquiry.java | Housing.java | Factory Classes | ApplicantUI.java | OfficerUI.java | ManagerUI.java | LoginUI.java | ChangePasswordUI.java | UIUtils.java UserUI.java BTOApp.java UserInterface.java | ProjectController.java | ApplicantController.java | EnquiryController.java | OfficerController.java | RegistrationController.java | UserManager.java | PasswordController.java IUserController.java | Authenticable.java BookingCapavble.java PersonalProfile.java | FileIOUtils | Testing | Javadocs | Overall individual contribution (by default, equal for every member)
*Kong Fook Wah | 100 | 0 | 20 | 25 | 30 | 50 | 100 | 20 | 0 | 0 | 10 | 80 | 80 | 80 | 45 | 50 | 100 | 55 | 60 | 30 | 90 | 45 | 33.333 | 50 | 100 | 100 | 50 | 0 | 0 | 100
Kris Khor Hai Xiang | 0 | 0 | 20 | 0 | 25 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lin Zeshen | 0 | 0 | 20 | 25 | 0 | 0 | 0 | 20 | 100 | 45 | 0 | 0 | 10 | 10 | 10 | 0 | 0 | 10 | 10 | 30 | 10 | 45 | 33.333 | 0 | 0 | 0 | 0 | 60 | 0 | 100
Mau Ze Ming | 0 | 100 | 20 | 25 | 45 | 0 | 0 | 20 | 0 | 10 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 10 | 10 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100
Zheng Nan | 0 | 0 | 20 | 25 | 0 | 50 | 0 | 20 | 0 | 45 | 90 | 20 | 10 | 0 | 45 | 50 | 0 | 35 | 20 | 30 | 0 | 0 | 33.333 | 50 | 0 | 0 | 50 | 40 | 100 | 100
Total (100%) | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
# Sheet 2 contains our Meeting logs
* Project Manager
Note :
To be filled and vetted by every team member. Email TA and Dr. Li fang, at the same time, keep all memebers in mailing loop.
(1) The purpose of this spreadsheet is to indicate individual contribution and work/task distributions in the project so that appropriate assessments can be given to individual.
(2) A piece of work can be any task required by the project. Eg coding of individual implementation code, setup task, testing, research task, etc.
(3) A piece of work is considered to be 100% completed upon submission for assessment and grading
(4) The percentage contribution by individual for each task is a judgement to be decided by team mates. (IT IS IMPORTANT THAT ALL MEMBER AGREED on the figures)
(5) Overall individual contribution (by deafult, equal for every member). i.e., if the overall assessment of the group project is 84. by default, everyone will get 84. for a student whose Overall individual contribution is 50%, wil get 42.

## Meeting Logs
S/N | Item | Class Involved? | Responsibility | Start Date | Expected Date | Progress | Remarks
1 | Week 9: Meeting on 21/3/2025
2 | First meeting: Make sure everyone is on the same page and set timeline for the project to be done
3 | Week 10: All features done and ready to be tested
4 | Week 11: Generate test case and refine class diagram and sequence Diagram
5 | Week 10: Meeting on 28/3/2025
6 | Able to view the list of projects (for open projects) | Applicant | Kris | 2025-03-28 | 2025-04-04 | 100% | Done by Kong, tested by zeshen | Today: | 2025-04-23
7 | Able to view the list of projects (for applied projects) | Applicant | Kris | 2025-03-28 | 2025-04-04 | 100% | Done by Kong, tested by zeshen
8 | View all projects | HDB Manager | Zheng Nan | 2025-03-28 | 2025-04-04 | 100%
9 | View all enquiries | HDB Manager | Kong | 2025-03-28 | 2025-04-04 | 100%
10 | Allowed to request withdrwal before/after flat booking | Applicant | Kris | 2025-03-28 | 2025-04-04 | 100% | Done by Kong, tested by zeshen
11 | Able to submit enquiries | Applicant | Zeshen | 2025-03-28 | 2025-04-04 | 100% |  | Todo: implement saving for enquiry
12 | Able to view all projects that he is handling | HDB Officer | Ze Ming | 2025-03-28 | 2025-04-04 | 100% | yet to test, testing done by zeshen
13 | Register to join a project if criterias are met | HDB Officer | Zeshen | 2025-04-06 | 2025-04-04 | 100% |  | Todo: implement saving for regisgtration
14 | Able to see status of registration | HDB Officer | Zeshen | 2025-03-28 | 2025-04-04 | 100%
15 | Able to apply for projects that he is not handling | HDB Officer | Zeshen | 2025-03-28 | 2025-04-04 | 100%
16 | Able to view,edit and delete enquiries | Applicant | Zeshen | 2025-03-28 | 2025-04-04 | 100%
17 | Approval for HDB Officer to be the project's officer | HDB Manager | Ze Ming | 2025-03-28 | 2025-04-04 | 100% | yet to test, testing done by zeshen
18 | Able to view and reply to enquiries he is handling | HDB Officer | Ze Ming | 2025-03-28 | 2025-04-04 | 100% | yet to test, testing done by zeshen
19 | Generate receipts for applicants with their booking details | HDB Officer | Kong | 2025-03-28 | 2025-04-04 | 100%
20 | Create, delete and edit BTO projects | HDB Manager | Zheng Nan | 2025-03-28 | 2025-04-04 | 100%
21 | Enter BTO projects information | HDB Manager | Zheng Nan | 2025-03-28 | 2025-04-04 | 100% | Subfeature of 15
22 | Toggle project visibility | HDB Manager | Zheng Nan | 2025-03-28 | 2025-04-04 | 100% | Subfeature of 15
23 | Able to book flat through HDB Officer | Applicant | Kris | 2025-03-28 | 2025-04-04 | 100% | Done by Kong, Yet to add booking logic
24 | Filter and view projects he created himself | HDB Manager | Zheng Nan | 2025-03-28 | 2025-04-04 | 100% | Subfeature of 18
25 | View pending and approved HDB Officer registration | HDB Manager | Ze Ming | 2025-03-28 | 2025-04-04 | 100% | yet to test, testing done by zeshen
26 | Approve or reject Applicant's application | HDB Manager | Ze Ming | 2025-03-28 | 2025-04-04 | 100%
27 | Generate a report of the list of applicants with their booking details (Similar to 14) | HDB Manager | Kong | 2025-03-28 | 2025-04-04 | 100%
28 | Able to apply for projects | Applicant | Kris | 2025-03-28 | 2025-04-04 | 100% | Done by Kong, yet to test it out
29 | View and reply to enquiries regarding project he is handling | HDB Manager | Kong | 2025-03-28 | 2025-04-04 | 100% | Possible refactoring: viewandReplytoenquiries() method in OfficerUI and ManagerUI
30 | Use filters to view projects | all | Zheng Nan | 2025-03-28 | 2025-04-04 | 100%
31 | Sequence Diagram | Document | Kris and Zeming | 2025-03-28 | 2025-04-04 | 100% | Done by Zeming
32 | Week 11: Meeting on 04/4/2025
33 | Focus on asking each other's progress, all features are almost done, most of the features have yet to be tested
34 | Week 12: Meeting on 11/4/2025 (F2F in lab)
35 | Single Responsibility Principle | Document |  | 2025-04-11 |  | 100% | Done by Kong: 19/4/2025
36 | Open/Closed Principle | Document |  | 2025-04-11 |  | 100% | Done by Kong: 19/4/2025
37 | Liskov Substitution Principle | Document |  | 2025-04-11 |  | 100% | Done by Kong: 19/4/2025
38 | Interface Segregation Principle | Document |  | 2025-04-11 |  | 100% | Done by Kong: 19/4/2025
39 | Dependency Inversion Principle | Document |  | 2025-04-11 |  | 100% | Done by Kong: 19/4/2025
40 | Week 13: Meeting on 18/4/2025 (Kris was absent)
41 | Finalised on details to present on the presentation day
42 | Check on what other test cases are needed to be tested
43 | Canva Presentation Slide | Document | All | 2025-04-18 | 2025-04-24 | 50%